## Sheet1
Product Backlog
Story ID | Name | Status | Size | Sprint | Priority | Comments | Team Members
1 | Set # of Turns | Postponed | 1 | 2 | Low | We made it so that there are 3 turns in a game by default. Perhaps in a leter update players will be able to change the number of turns per game. | Marqwon M.
2 | Roll Dice | Completed | 1 | 2 | High |  | Michael Fraiz
3 | Reroll Dice | Completed | 1 | 3 | Medium |  | Michael Saul
4 | Pair Dice | Completed | 1 | 2 | High |  | Mauricio
5 | Select Dice Pairs to Use In Each Round | Completed | 1 | 2 | High |  | Manuel
6 | Use Hindrance | Completed | 1 | 3 | Medium
7 | Use Dice-Block! | Completed | 1 | 3 | Medium
8 | Use Lucky Dice! | Completed | 1 | 3 | Medium
9 | Cancel an Action being Performed | Completed | 1 | 3 | Medium
10 | Select Player to Perform Action upon | Completed | 1 | 3 | Medium
11 | Select Round to Perform Action | Completed | 1 | 3 | Medium
12 | Round Win Condition | Completed | 1 | 2 | High
13 | See Point Scores for current game | Completed | 1 | 2 | High
14 | See my Game Statistics | Completed | 1 | 3 | Low
15 | See Top Scores/Stats | Completed | 1 | 3 | High | The assumption is that a name is unique for a user but as of yet there is no way to ensure this assumption. This is something to do fro a future update.
16 | Compare Dice Pairs | Completed | 1 | 2 | High
17 | Game Win Condition | Completed | 1 | 2 | High
18 | Select starting points for game | Completed | 1 | 2 | Low
19 | Enter Name | Completed | 1 | 2 | Medium