## Sheet1
Product Backlog
Story ID | Name | Status | Size | Sprint | Priority | Comments | Team Members
1 | Set # of Turns | Completed | 1 | 2 | Low |  | Marqwon M.
2 | Roll Dice | Completed | 1 | 2 | High |  | Michael Fraiz
3 | Reroll Dice | In Progress | 1 | 3 | Medium |  | Michael Saul
4 | Pair Dice | Completed | 1 | 2 | High |  | Mauricio
5 | Select Dice Pairs to Use In Each Round | Completed | 1 | 2 | High |  | Manuel
6 | Use Hindrance | In Progress | 1 | 3 | Medium
7 | Use Dice-Block! | In Progress | 1 | 3 | Medium
8 | Use Lucky Dice! | In Progress | 1 | 3 | Medium
9 | Cancel an Action being Performed | In Progress | 1 | 3 | Medium
10 | Select Player to Perform Action upon | In Progress | 1 | 3 | Medium
11 | Select Round to Perform Action | In Progress | 1 | 3 | Medium
12 | Round Win Condition | Completed | 1 | 2 | High
13 | See Point Scores for current game | Completed | 1 | 2 | High
14 | See my Statistics | In Progress | 1 | 3 | Low
15 | See Top Scores/Stats | In Progress | 1 | 3 | High
16 | Compare Dice Pairs | Completed | 1 | 2 | High
17 | Game Win Condition | Completed | 1 | 2 | High
18 | Select starting points for game | Completed | 1 | 2 | Low
19 | Enter Name | Completed | 1 | 2 | Medium